## WorkToDo
S.No. | Suggestion | Implementation | Suggested By | Priority | Assigned To | Status | Comments
1 | Users should have ability to select tests for execution if they don't want to run the complete TestSet | Update ExecuteTestSet.vbs to check if testFolder in TestSet.xlsx has a keyword then go and execute tests from the MultipleTestFodlers sheet and execute the tests that are marked Yes | Shweta | Medium | Shweta
2 | Change TestLab -> TestSet -> deviceOSVersion column text format | Changed text format of the cell to display exactly whta is entered eg, 6.0 , 7.0 etc. | Shweta | Minor | Shweta | Done
3 | Configuration managment tool identification. | Identification of configuration managment tool to save resources at some shared location. | Nitesh | High | Nitesh
4 | Updating existing scripts | Need to modify steps which are not relevant. | Shweta | High |  |  | Pradeep/Shweta/Jaishree/Naveen
5 | Add and implement new methods in scripts | Create functions for methods which are not automated and add there respective steps in scripts. | Shweta | High |  |  | Jaishree/Shweta
6 | Add additional folder in \tests\trust for Demo script | Demo script folder will have demo scripts. | Shweta | Minor
7 | Remove ALM references from scripts | Remove ALM references from scripts | Naveen | High | Jaishree | Done
8 | Pause , stop and continue qtp execution. | Create shortcuts for script pause , continue and stop. | Shweta | Medium | Nitesh |  | Linked to Action item 3
9 | Device not getting connected automatically if viewer gets disconnected | Device not getting connected automatically if viewer gets disconnected | Jaishree | High |  |  | Talk to Jaishree to get more info - Nitesh
10 | Instead of giving complete folder path in testFolder , give application name only | \Test\Trust path will be fixed and rest of the script path will be concatenated to it at the time of run time eg. If testFolder value is Phonelookup and deviceOS is Android then it will pick scripts from \test\trust\Android\Phonelookup | Shweta | Minor |  |  | As discussed, we want to keep the current implementation.
11 | Remove appId column from the TestSet sheet | Already mentioned in Multipletest folder sheet. | Shweta | Minor |  |  | As discussed, we want to keep the current implementation.

## WBS
S.No. | Task | Assigned To | Estimated Effort (Hrs.) | Start Date | End Date | WorkToDo Action Item Ref. | Misc.
1 | Modification - Android Scripts | Pradeep | 41 | 2015-10-12 |  | 4 | 2 Hrs/Day
2 | Modification - iOS Scripts | Shweta | 40 | 2015-10-12 |  | 4 | 3 Hrs/Day
3 | Modification - Web Scripts | Jaishree | 44 | 2015-10-12 |  | 4 | 3 Hrs/Day
4 | New Scripts and Methods |  |  | 2015-10-08 |  | 5
4.1 | MobiWebview | Shweta | 5 | 2015-10-08 | 2015-10-08
4.2 | MobiPicker (iOS 8) | Shweta | 6 | 2015-10-09 | 2015-10-09
4.3 | MobiDatePicker (iOS 8 Mode2) | Shweta | 6 | 2015-10-09 | 2015-10-09
4.4 | IsOccluded | Jaishree | 5 | 2015-10-08 | 2015-10-09
4.5 | Draw | Shweta | 4 | 2015-10-09 | 2015-10-09
4.6 | SetGlobalOffset | Naveen | 4 | 2015-10-08 | 2015-10-09
4.7 | EvaluateScript | Naveen | 6 | 2015-10-08 | 2015-10-09
4.8 | Childobject (Recursive scenario) | Jaishree | 3 | 2015-10-09 | 2015-10-09
5 | CI Tool - Identification of configuration managment tool to save resources at some shared location. | Nitesh | 18 | 2015-10-08 |  | 3 | 4 Hrs/Day
6 | Users should have ability to select tests for execution if they don't want to run the complete TestSet | Shweta |  |  |  | 1
7 | Pause , stop and continue qtp execution. | Nitesh |  |  |  | 8
8 | Add additional folder in \tests\trust for Demo script |  |  |  |  | 6
9
10
11
12
13
14
15
16
17
18
19
20

## Task Details
S.No. | Script | Status | Task Pending | Time Required | S.No. | Script | Status | Task Pending | Time Required | S.No. | Script | Status | Task Pending | Time Required | S.No. | New Scripts and Methods | Status | Time Required |  | Status
1 | Android -> MobiButton | Update | a) Remove Click with negative and zero co-ordinate steps. b) Update run time property list. c) Include Isoccluded method( If applicable) d) Add steps for Sync method. | 4 hrs | 1 | iOS -> MobiButton | Update | a) Remove Click with negative and zero co-ordinate steps. b) Update run time property list. c) Include Isoccluded method( If applicable) d) Add steps for Sync method. | 4 hrs | 1 | MobiWebview | New | All | 8 hrs | 1 | MobiWebview | Partially done | 5 hrs | Shweta
2 | Android -> MobiDevice | Update | a) Add 4 steps for Rotate method (Positive) and 2 steps for Negative scenario. B) Add steps for Childobjective with Recursive value (Covering both Recursive set to True or False) c) Add steps for Draw method (Performing swipe , click etc) d) Add steps for Sync method. e) Add steps for StepGlobalOffset method. f) Modify Runtime property list. g) Remove negative and Zero co-ordinates steps from Click , DblClick and Longclick methods. | 8 hrs | 2 | iOS -> MobiDevice | Update | a) Add 4 steps for Rotate method (Positive) and 2 steps for Negative scenario. B) Add steps for Childobjective with Recursive value (Covering both Recursive set to True or False) c) Add steps for Draw method (Performing swipe , click etc) d) Add steps for Sync method. e) Add steps for StepGlobalOffset method. f) Modify Runtime property list. g) Remove negative and Zero co-ordinates steps from Click , DblClick and Longclick methods. | 8 hrs | 2 | MobiWebbutton | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 2 | MobiPicker (iOS 8) | New | 6 hrs | Shweta
3 | Android -> MobiCheckbox | Update | a) Update run time property list. B) Remove negative and zero co-ordinate steps from Click method. C) Add steps for Sync method d) Include Isoccluded method( If applicable) | 3 hrs | 3 | iOS -> MobiCheckbox | Update | a) Update run time property list. B) Remove negative and zero co-ordinate steps from Click method. C) Add steps for Sync method d) Include Isoccluded method( If applicable) | 3 hrs | 3 | MobiWebRadiobutton | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 3 | MobiDatePicker (iOS 8 Mode2) | New | 6 hrs | Shweta
4 | Android -> DateTimePicker | Update | a) Remove obselete steps from Select method. B) Remove Click with negative and zero co-ordinates steps. C) Update runtime property list. D) Add steps for Sync method e) Include Isoccluded method( If applicable) | 5 hrs | 4 | iOS -> Picker | Update | a) Remove obselete steps from Select method. B) Remove Click with negative and zero co-ordinates steps. C) Update runtime property list. D) Add steps for Sync method e) Include Isoccluded method( If applicable) | 5 hrs | 4 | MobiWebCheckbox | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 4 | IsOccluded | New | 5 hrs | Jaishree
5 | Android -> MobiEdit | Update | a) Remove negative and zero co-ordinates steps for Click , dblCLick and Longclick methods b) Update runtime property list. C) Add steps for Send method d) Add steps for Sync method. E) Include Isoccluded method( If applicable) | 5 hrs | 5 | iOS -> MobiEdit | Update | a) Remove negative and zero co-ordinates steps for Click , dblCLick and Longclick methods b) Update runtime property list. C) Add steps for Send method d) Add steps for Sync method. E) Include Isoccluded method( If applicable) | 5 hrs | 5 | MobiDropdown | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 5 | Send | Done
6 | Android -> MobiDropdown | Update | a) Remove negative and Zero co-ordinate steps. B) Update runtime property list. C) Add steps for Sync method. D)Include Isoccluded method( If applicable) | 4 hrs | 6 | iOS -> MobiSegment | Update | a) Remove negative and Zero co-ordinate steps. B) Update runtime property list. C) Add steps for Sync method. D)Update select method steps and add steps for selecting segment using value | 4 hrs | 6 | MobiWebEdit | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 6 | Sync | Done
7 | Android -> MobiElement | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 7 | iOS -> MobiElement | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 7 | MobiWebTable | Update | a) Check steps for scrollintoview b) Update runtime property list. | 4 hrs | 7 | Draw | Partially done | 4 hrs | Shweta
8 | Android -> MobiList | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 8 | iOS -> MobiList | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 8 | MobiWebLink | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4hrs | 8 | Rotate | Done
9 | Android -> MobiSwitch | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 9 | iOS -> MobiSlider | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 9 | MobiWebElement | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 9 | SetGlobalOffset | New | 4 hrs | Naveen | Done
[5 empty] | 10 | iOS -> MobiSwitch | Update | a) Remove negative and zero co-ordinates steps for Click method. B) Add steps for Sync method. C) Update runtime property list d) Include Isoccluded method( If applicable) | 4 hrs | 10 | MobiWebImage | Update | a) Check steps for scrollintoview b) Update runtime property list. C) Add step for click using evaluatescript method d) Add step for fetching runtime property value using evaluatescript method. | 4 hrs | 10 | EvaluateScript | New | 6 hrs | Naveen | Done
[15 empty] | 11 | Childobject (Recursive scenario) | New | 3 hrs | Jaishree
[15 empty] | 12 | Scale | New | 3 hrs | Shweta